## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Project Introduction & Problem Understanding (Stock & ETF Signals) | MUST HAVE | No Dependency | Your Name | 3- Completed
S1 | S1 | US-002 | Workflow Design & Architecture Planning (ML + APIs + Dashboard) | MUST HAVE | Lucidchart / Draw.io | Your Name | 3- Completed
S2 | S2 | US-003 | Environment Setup & API Integration (Yahoo Finance / Alpha Vantage) | MUST HAVE | Python, APIs | Your Name | 3- Completed
S2 | S2 | US-004 | Data Cleaning & Feature Engineering for Market Data | MUST HAVE | Pandas, NumPy | Your Name | 3- Completed
S3 | S3 | US-005 | ML Model Development (Random Forest, LSTM, Gradient Boosting) | MUST HAVE | Scikit-learn, TensorFlow | Your Name | 3- Completed
S4 | S4 | US-006 | Signal Generation Logic (Buy/Sell/Hold Predictions) | MUST HAVE | ML Models | Your Name | 3- Completed
S5 | S5 | US-007 | Backtesting Engine Implementation (Historical Data Testing) | MUST HAVE | Historical Data APIs | Your Name | 2- In Progress
S6 | S6 | US-008 | Performance Metrics Calculation (Sharpe Ratio, Drawdown, Win Rate) | SHOULD HAVE | Backtesting Module | Your Name | 2- In Progress
S7 | S7 | US-009 | Real-Time Alert System (Email / Slack Notifications) | SHOULD HAVE | SMTP / Slack API | Your Name | 2- In Progress
S8 | S8 | US-010 | Dashboard Development (Streamlit / Dash Visualization) | MUST HAVE | Streamlit / Plotly | Your Name | 2- In Progress
S9 | S9 | US-011 | Integration of All Modules (End-to-End Workflow) | MUST HAVE | All Modules | Your Name | 2- In Progress
S10 | S10 | US-012 | Testing, Deployment & Final Presentation (Render/Cloud) | MUST HAVE | Render / Cloud | Your Name | 2- In Progress

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7