## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Project Introduction & Problem Understanding (Stock & ETF Signals) | MUST HAVE | No Dependency | Mosra Sanjana Reddy | 3- Completed
S1 | S1 | US-002 | Workflow Design & Architecture Planning (ML + APIs + Dashboard) | MUST HAVE | Lucidchart / Draw.io | Mosra Sanjana Reddy | 3- Completed
S2 | S2 | US-003 | Environment Setup & API Integration (Yahoo Finance / Alpha Vantage) | MUST HAVE | Python, APIs | Mosra Sanjana Reddy | 3- Completed
S2 | S2 | US-004 | Data Cleaning & Feature Engineering for Market Data | MUST HAVE | Pandas, NumPy | Mosra Sanjana Reddy | 3- Completed
S3 | S3 | US-005 | ML Model Development (Random Forest, LSTM, Gradient Boosting) | MUST HAVE | Scikit-learn, TensorFlow | Mosra Sanjana Reddy | 3- Completed
S4 | S4 | US-006 | Signal Generation Logic (Buy/Sell/Hold Predictions) | MUST HAVE | ML Models | Mosra Sanjana Reddy | 3- Completed
S5 | S5 | US-007 | Backtesting Engine Implementation (Historical Data Testing) | MUST HAVE | Historical Data APIs | Mosra Sanjana Reddy | 2- In Progress
S6 | S6 | US-008 | Performance Metrics Calculation (Sharpe Ratio, Drawdown, Win Rate) | SHOULD HAVE | Backtesting Module | Mosra Sanjana Reddy | 2- In Progress
S7 | S7 | US-009 | Real-Time Alert System (Email / Slack Notifications) | SHOULD HAVE | SMTP / Slack API | Mosra Sanjana Reddy | 2- In Progress
S8 | S8 | US-010 | Dashboard Development (Streamlit / Dash Visualization) | MUST HAVE | Streamlit / Plotly | Mosra Sanjana Reddy | 2- In Progress
S9 | S9 | US-011 | Integration of All Modules (End-to-End Workflow) | MUST HAVE | All Modules | Mosra Sanjana Reddy | 2- In Progress
S10 | S10 | US-012 | Testing, Deployment & Final Presentation (Render/Cloud) | MUST HAVE | Render / Cloud | Your Name | 2- In Progress

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 30 | 1 | 2 | 2 | 3 | 4 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 0
SPRINT 1 BACKLOG
US-001 | T-001 | Understand project problem statement | 2026-01-02 | 2026-05-02 | Mosra Sanjana Reddy | Analysis | Completed | 6 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-002 | Research stock & ETF signals | 2026-06-02 | 2026-12-02 | Mosra Sanjana Reddy | Research | Completed | 8 | 0 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-003 | Design system architecture | 13-02-2026 | 25-02-2026 | Mosra Sanjana Reddy | Design | Completed | 10 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
US-002 | T-004 | Create workflow diagram | 26-02-2026 | 2026-05-03 | Mosra Sanjana Reddy | Design | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 1 | Initial confusion in project understanding | Reviewed project documentation
S1 | Day 2 | Difficulty in identifying data sources | Explored financial APIs like Yahoo Finance
S1 | Day 3 | Lack of clarity in ETF concepts | Studied online tutorials and references
S1 | Day 4 | Understanding trading signals was complex | Referred to articles and examples
S1 | Day 5 | Difficulty in mapping requirements | Broke down problem into smaller tasks
S1 | Day 6 | Selecting proper tools for design | Chose Draw.io for workflow creation
S1 | Day 7 | Minor confusion in architecture design | Revised system components
S1 | Day 8 | Difficulty in structuring workflow | Improved diagram step-by-step
S1 | Day 9 | Time management issue | Allocated fixed hours daily
S1 | Day 10 | Small design inconsistencies | Refined architecture
S1 | Day 11 | No major issues | Continued work smoothly
S1 | Day 12 | No major issues | Progressed as planned
S1 | Day 13 | Minor doubts in final design | Cross-checked design
S1 | Day 14 | No issues | Completed sprint successfully

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2026-01-02 | 2026-05-03 | Mosra Sanjana Reddy | Start structured planning before tasks | Stop delaying initial research | Continue consistent daily progress | Created proper task schedule
2 | S1 | 2026-01-02 | 2026-05-03 | Mosra Sanjana Reddy | Start documenting learning daily | Stop unorganized workflow | Continue using reliable resources | Maintained notes for clarity
3 | S1 | 2026-01-02 | 2026-05-03 | Mosra Sanjana Reddy | Start breaking tasks into smaller steps | Stop handling tasks randomly | Continue step-by-step execution | Improved task tracking
4 | S1 | 2026-01-02 | 2026-05-03 | Mosra Sanjana Reddy | Start better time management | Stop spending too much time on one task | Continue maintaining deadlines | Allocated fixed time slots
5 | S1 | 2026-01-02 | 2026-05-03 | Mosra Sanjana Reddy | Start validating design early | Stop last-minute corrections | Continue refining design | Reviewed work regularly